## Ch7_P32
Taylor, Introduction to Management Science: Chapter 7, Problem 32
Branches | Flights | Capacity | Nodes | Network
1 to 2 | 6 | 10 | 1 | 18
1 to 3 | 5 | 5 | 2 | 0
1 to 4 | 7 | 7 | 3 | 0
2 to 4 | 0 | 7 | 4 | 0
2 to 6 | 6 | 8 | 5 | 0
3 to 4 | 0 | 4 | 6 | 0
3 to 5 | 5 | 6 | 7 | 0
4 to 6 | 0 | 4 | 8 | -18
4 to 7 | 3 | 7
4 to 8 | 4 | 4
5 to 7 | 5 | 5
6 to 8 | 6 | 6
7 to 8 | 8 | 8
8 to 1 | 18
Maximum flow: 18 flights

## Ch8_P2
Taylor, Introduction to Management Science: Chapter 8, Problem 2
Activity | Predecessor | Time | Early Start | Early Finish | Late Start | Late Finish | Slack
1 | 0 | 3 | 0 | 3 | 12 | 15 | 12
2 | 0 | 7 | 0 | 7 | 0 | 7 | 0
3 | 1 | 2 | 3 | 5 | 15 | 17 | 12
4 | 2 | 5 | 7 | 12 | 11 | 16 | 4
5 | 2 | 6 | 7 | 13 | 7 | 13 | 0
6 | 4 | 1 | 12 | 13 | 16 | 17 | 4
7 | 5 | 4 | 13 | 17 | 13 | 17 | 0
Activity | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1
2
3
4
5
6
7

## Ch8_P4-5
Taylor, Introduction to Management Science: Chapter 8, Problem 4 & 5
Path |  |  | Length
1 | Start > 1 > 3 > 6 > 7 |  | 18
2 | Start > 2 > 4 > 6 > 7 |  | 20
3 | Start > 2 > 5 > 7 |  | 16
The path with maximum length or critical path is Path 2.
Activity | Time | Early Start | Early Finish | Late Start | Late Finish | Slack
1 | 7 | 0 | 7 | 2 | 9 | 2
2 | 10 | 0 | 10 | 0 | 10 | 0
3 | 6 | 7 | 13 | 9 | 15 | 2
4 | 5 | 10 | 15 | 10 | 15 | 0
5 | 4 | 10 | 14 | 14 | 18 | 4
6 | 3 | 15 | 18 | 15 | 18 | 0
7 | 2 | 18 | 20 | 18 | 20 | 0
After calculating the slack for each activity, critical path is still Path 2.

## Ch8_P15
Taylor, Introduction to Management Science: Chapter 8, Problem 15
|  |  | Time Estimates |  |  | Expected Time | Variance
Activity | Description | Predecessor | a | m | b | t = (a+4m+b)/6 | v = ((b-a)/6)^2 | Activity | Early Start | Early Finish | Late Start | Late Finish | Slack
a | Position recruiting | — | 5 | 8 | 17 | 9 | 4 | a | 0 | 9 | 0 | 9 | 0
b | System development | — | 3 | 12 | 15 | 11 | 4 | b | 0 | 11 | 7 | 18 | 7
c | System training | a | 4 | 7 | 10 | 7 | 1 | c | 9 | 16 | 11 | 18 | 2
d | Equipment training | a | 5 | 8 | 23 | 10 | 9 | d | 9 | 19 | 9 | 19 | 0
e | Manual system test | b, c | 1 | 1 | 1 | 1 | 0 | e | 16 | 17 | 18 | 19 | 2
f | Preliminary system changeover | b, c | 1 | 4 | 13 | 5 | 4 | f | 16 | 21 | 26 | 31 | 10
g | Computer–personnel interface | d, e | 3 | 6 | 9 | 6 | 1 | g | 19 | 25 | 19 | 25 | 0
h | Equipment modification | d, e | 1 | 2.5 | 7 | 3 | 1 | h | 19 | 22 | 21 | 24 | 2
i | Equipment testing | h | 1 | 1 | 1 | 1 | 0 | i | 22 | 23 | 24 | 25 | 2
j | System debugging and installation | f, g | 2 | 2 | 2 | 2 | 0 | j | 25 | 27 | 31 | 33 | 6
k | Equipment changeover | g, i | 5 | 8 | 11 | 8 | 1 | k | 25 | 33 | 25 | 33 | 0
[12 empty] | Critical Path: | a-d-g-k
[12 empty] | Expected Completion: | 33
[12 empty] | Variance: | 15
[12 empty] | Standard Deviation: | 3.873
[12 empty] | Probability: | 96.46% | 0.96465
(Probability that project will be completed in 40 weeks or less.)